## Lists (hidden)
Pending | Pending | Member | Smoke | Amutha
Approved | Approved | Claims | Regression | Ajim
Rework | Rejected | Provider | Negative | Komali
Blocked |  | Other | Sanity | Arun M

## Weekly Tracker
Test Automation Quality Gate Weekly Tracker
Tuesday = Design Gate Review ¦ Thursday = Code Gate Review ¦ Backup Approver = Arun M
Week Start | TC ID | Test Case Name | Module | QA Owner | Type | Design Gate Status | Design Reviewer | Design Review Date | Code Gate Status | Code Reviewer | Code Review Date | Final Status | Approved By | Execution Ready | Comments | Report Link
2026-04-20 | TC001 | Member enrollment validation | Member | QA 1 | Smoke | Approved | Amutha | 2026-04-21 | Pending |  |  | Pending |  |  | Waiting for scripting
2026-04-20 | TC002 | Claim status API negative scenario | Claims | QA 2 | Regression | Approved | Ajim | 2026-04-21 | Approved | Komali | 2026-04-23 | Approved | Komali |  | Ready for CI
2026-04-20 | TC003 | Provider search UI validation | Provider | QA 3 | Regression | Rework | Komali | 2026-04-21 | Pending |  |  | Pending |  |  | Locator stability issue

## Dashboard
Quality Gate Dashboard
Weekly review cadence: Tuesday (Design) ¦ Thursday (Code)
Total Test Cases |  | Design Approved |  | Code Approved | Final Approved
Pending Reviews |  | Blocked / Rework
QA Owner Summary |  |  |  |  | Module Summary |  |  |  | Status Summary
QA Owner | Total TCs | Design Approved | Code Approved | Final Approved | Module | Total TCs | Approved | Pending/Rework | Status | Count
QA 1 |  |  |  |  | Member |  |  |  | Approved
QA 2 |  |  |  |  | Claims |  |  |  | Pending
QA 3 |  |  |  |  | Provider |  |  |  | Rework
QA 4 |  |  |  |  | Other |  |  |  | Blocked
QA 5
QA 6

## Instructions
How to Use This Workbook
1. Update one row per test case in the Weekly Tracker sheet.
2. Tuesday: update Design Gate Status and reviewer.
3. Thursday: update Code Gate Status and reviewer.
4. Final Status should be Approved, Pending, or Rejected.
5. Execution Ready is auto-calculated.
6. Dashboard updates automatically from tracker data.
7. Approved reviewers: Amutha, Ajim, Komali. Backup: Arun M.